| COSCAP South Asia | Cooperative Development of Operational Safety & |  |
| --- | --- | --- |
|  | Continuing Airworthiness Programme |  |

26th COSCAP-SA STEERING COMMITTEE MEETING

Annual Work Programme 2018

Discussion Paper 4 (DP-4)

(Presented by CTA)

SUMMARY The purpose of this paper is to present the proposed COSCAP-SA 2018 Annual Work Plan (AWP). The proposed Work Plan has been developed based on the available resources and the priorities established by the COSCAP-SA Steering Committee. The COSCAP-SA has available one Chief Technical Advisor (CTA) and one Office Secretary Emphasis in 2018 will be placed, in part, on ANS and Aerodrome training. A list of high and medium priority courses, which will be delivered in 2018, is located in Appendix III. As per the new proposed COSCAP SA Performance indicators and targets, 100% of high priority courses and at least 50% of the medium priority courses will be delivered in 2018. A Summary Report by Activity Area for COSCAP-SA appears at Appendix II. This report will be updated and presented at subsequent Steering Committee meetings for review and comments as an adjunct to the Work Plan.

1	Background

1.1	Pursuant to the Institutional Framework and Procedures Manual (IFAPM), Annual Work Programmes need to be prepared by the CTA.

2 	Discussion

2.1 	Steering Committee Meetings:  The CTA will be required to prepare numerous Discussion Papers for review by the SC Meeting in order that they can establish the priorities for the programme for the period following the previous 25th Meeting of the Steering Committee and to update Members on recent developments.

2.2 	Safety Team Meetings:  With the establishment of the ICAO Regional Aviation Safety Group (RASG), and the Asia-Pacific Regional Aviation Safety Team (APRAST), COSCAP-SA will be required to participate in the RASG, APRAST and SARAST meetings to enable meaningful consideration of safety issues.  In addition, COSCAP-SA will support Member States to implement the safety enhancement priorities in the areas of LOC, CFIT and Runway Safety, including associated APRAST Safety Tools that are emerging from the RASG/ APRAST activities.

2.3	Technical Assistance:  COSCAP-SA is planning to provide in-country Technical Assistance (TA) to member States on a “on demand basis” as depicted on the Technical Assistant Matrix (TAM) located in Appendix I of this paper. Technical Assistance (TA) missions (2018) which have already been requested by States have been scheduled on the TAM. States who have not requested TA, to date, have been each assigned 2 “adhoc” TA mission slots throughout the year in the case the need arises accordingly. Note that the dates on the TAM are for planning purposes only. States are requested to notify the CTA preferably 3 months in advance regarding the TA related activities, which COSCAP-SA is requested to assist with. The Work Plan is subject to revision and will be updated periodically throughout the year.

2.4	Training and Programme Support: Where appropriate, training will be conducted in close coordination with COSCAP-SEA, COSCAP-NA and ICAO Regional Office Bangkok. In addition, the COSCAP SA will continue to work with the EU SA Aviation Partnership Project for the establishment of a COSCAP SA – EASA – SARI Joint Activity Plan - 2018. The final version (including Course outlines) and the schedule of the Joint Activity Plan should be available in February 2018 once approval has been received from the EC. Several courses from the previous year joint activity plan (2017) have spilled over into early 2018. In addition, a few additional courses (i.e. SMS and SSP Implementation courses) have also been added to take place early 2018.

2.5	The Annual Work Plan (AWP) - 2018 for COSCAP SA training courses has been prioritized as high and medium priority. The prioritization has been done in accordance to the highest demands by Member States. As per the new proposed COSCAP SA Performance indicators and targets, 100% of high priority courses and at least 50% of the medium priority courses will be delivered in 2018.  Courses not conducted during this period, will be forwarded into the next time period accordingly. A list of high and medium priority courses can be found in Appendix III. Note that the AWP is derived from a Master Matrix which contains all of the Member States desired/wishlisted courses (Appendix V).

2.6	In 2018, more emphasis will done on training related to Air Navigation Services (ANS) and Aerodromes (AGA) as these two areas have low EIs throughout the region.

2.7	 Due to the difficulty in obtaining “in country” training for Pakistan, the COSCAP SA will out-source courses with training service providers and/or private contractors that have no security restriction for travel into Pakistan. Pakistan CAA has provided a list (Appendix IV) of top priority courses, which will be used to schedule “in country” courses as feasibly possible. Note that some of these courses are already on the 2018 AWP as high and/or medium priority courses.

2.8	Member States may request training in areas, which are not mentioned in the Work Plan. Requests for such training should be made to the COSCAP-SA office as early as possible so that steps may be taken to provide such training depending on the availability of resources. Note: this will not prevent courses from being planned and delivered during this period. It is more for the purpose of managing and prioritizing the CTA’s time.

3	Summary Report by Activity Area for COSCAP-SA

3.1	The Summary Report by Activity Area (Appendix IV of this paper) is designed to map and track specific programme activity and feed into the COSCAP-SA Work Plan. While it is understood that Member needs are dynamic in some areas, the focus of the Summary Report is on the priorities as defined in the Programme Document and the strategic priorities of the GASP. The Summary Report will be presented to the Steering Committee on an annual basis along with the Work Plan and adjusted as necessary to meet the needs of the Member States.

4	Actions of the Meeting

4.1	The COSCAP-SA Steering Committee is invited to review the proposed Work Plan and the Summary Report by Activity Area and take decisions on the priorities for 2018. Supporting documents can be found in the Appendices Folder attached to this DP.

4.2	Based on the decisions of the Steering Committee, the CTA is to finalize the Work Plan for 2018, adjust the Summary Report and forward to Members for review, comment and confirmation as appropriate.

| MEMBER | JAN 2018 | FEB 2018 | MAR 2018 | APR 2018 | MAY 2018 | JUN 2018 | JUL 2018 | AUG 2018 | SEP 2018 | OCT 2018 | NOV 2018 | DEC 2018 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Bangladesh |  | Executive SMS Part II/III SARI OPS/FCL |  |  |  | SARI OPS/FCL |  |  |  | SARI OPS/FCL |  |  |
| Bhutan | SARI OPS/FCL | Executive SMS Part II/III | RNP AR OPS EVAL | ANS Expert – Airspace reclassification and Safety Risk Assessment AGA Expert – Implementation Mission | RCI Audits on Drukair, and Bhutan Airlines | RCI Audit on Bhutan Helicopters |  |  |  |  |  |  |
| India |  | Executive SMS Part II/III |  |  |  |  | TBD |  |  | TBD |  |  |
| Sri Lanka |  | Executive SMS Part II/III |  |  | TBD |  |  | TBD |  |  |  |  |
| Maldives |  | Executive SMS Part II/III |  |  |  | TBD |  |  |  |  |  | TBD |
| Nepal |  | Executive SMS Part II/III |  |  |  |  |  | TBD |  |  | TBD |  |
| Pakistan |  | Executive SMS Part II/III |  |  |  |  | TBD |  |  |  | TBD |  |
| Regional Events | 26th SCM |  | SARAST APRAST (telecom) | CTA on home leave in Canada |  | NC meeting SARAST |  | 27th SCM | CTA on Leave for two weeks |  | APRAST |  |
| ALL DATES ARE TENTATIVE CTA = Chief Technical Advisor – Flight Operations | M-APRAST – Maintenance APRAST | APRAST = Asia Pacific Regional Aviation Safety Team |
| RAI = Regional Airworthiness Inspector | SC = Steering Committee | DG = Dangerous Goods |
| AGA = Aerodrome | DGAP = Director General Asia Pacific | AME = Aviation medical examiner |
| CS = Cabin Safety | T = Tentative | SMS = Safety Management Systems |

Summary Report by Activity Area for COSCAP-SA 2016-2017

At this and future Steering Committee Meetings the CTA will present the work proposed and accomplished within the following areas for review and comment:

- Effective Safety Oversight (e.g. Legislation, Regulation, SARPS, USOAP, CAP, etc.)

- Safety Management (e.g. SSP, SMS,)

- Capacity Building (e.g. Training, Seminars, Workshops, Experts, etc.)

- Safety Enhancement (e.g. Safety team work, Implementation support)

- Administration

- Cooperation

| No. | Initiatives | Brief Description | Activity | Status |
| --- | --- | --- | --- | --- |
|  | EFFECTIVE SAFETY OVERSIGHT |  |  |  |
| 1 | USOAP Corrective Action Plan Follow-up for all States | Review of CAP implementation status Review of CC & SAAQ status as part of on-site support Updating/Implementation of CAPs Facilitation with ICAO Regional resources Engagement of experts as needed & possible States who have an SSC shall receive priority (Nepal) | Delivered on-demand from Members States To be conducted as part of regular missions Member States to identify needed expertise | On Going Conducted two RCI Audits in Nepal with FOI, AIR and PEL experts deployed to assist with SSC resolution Reviewed Bhutan PQs in OPS and PEL Special project requested to the EU SA Project for TA to Bhutan for regulatory review and implementation of SARI OPS and FCL. NOTE: This consist of the foundation required to resolve most USOAP CAPs/PQs Three workshops held so far for the SARI OPS and FCL implementation |
| 2 | USOAP –CMA support for all States. | - Briefing & familiarization for Management - Support for transition to EFoD - Training and OJT for NCMC and lead technical inspections - Use of CMA Framework with personnel - Assistance with the development of related procedures for CAP approval prior to posting to CMA framework - Identify possible CAPs where COSCAP could assist in providing evidence for validation by ICAO - Support Member’s self-assessment (ex. Annex 19) for new PQs as required | Delivered on-demand from Members States To be conducted as part of regular missions Member States to identify needed expertise | On Going |
|  | SAFETY MANAGEMENT |  |  |  |
| 3 | SSP | SSP Concept training and support Note: There is a need for COSCAP SA Member States to coordinate and share their experiences through a workshop format | On-demand from Members States Note: The CTA will prepare workshops as required to provide an opportunity for States to share their SSP experiences. This also includes their experience in developing Safety Performance Indicators | SSP Implementation Course delivered November 7-11, 2016 in Bangkok. During the Basic SMS course, SSP module presented for discussion. EASA SMS/SSP Implementation course delivered in India, Bangladesh, Bhutan and Sri Lanka |
| 4 | SMS Basic workshop Advance workshop Executive workshop Specific SMS Courses | SMS Concept training and support Basic and advance courses are being delivered by the CTA. In addition executive version of the SMS programme is also available on demand. | On Demand from Member States Note: The CTA will prepare workshops as required to provide an opportunity for States to share their SMS experiences. The respective operators are strongly encouraged to participate as well if possible. Workshops may be customized also to meet specific demands Specific courses such as SMS – Maintenance, Aerodromes, ANS, Manufacturers, Flight Training Units etc may also be made available upon request. | Bhutan, Pakistan, India, Maldives and Sri Lanka have received SMS Basic courses. Bhutan, Pakistan and Sri Lanka have received Executive Part I courses Executive SMS Part II and III are scheduled in February 2018 Bangladesh, Bhutan, India and Sri Lanka have received the EASA SMS/SSP Implementation (including OJT). Note: this is the advance course which follows the Basic SMS course. |
|  | CAPACITY BUILDING TRAINING COURSES |  |  |  |
| 5 | Reliability Programme | Technical training required for airworthiness inspectors | Discussions are taking place with EASA through their South Asia project to address this training need in order to avoid duplication | Sri Lanka has received the EASA Reliability Programme Course. More States to receive the course in 2018 |
| 6 | PBN Ops Approval | Technical Training for the approval of PBN - Operations | This course has already been delivered in October 2016 in Beijing. All South Asia States were invited to attend. A Second course may be required towards the end of the 2016-2017 period. | PBN OPS approval course to be scheduled in 2018 RNP AR TA support provided to Bhutan for new RNP AR - Paro approach |
|  | ETOPS/RVSM/RNP/ CAT II/III OPS Air and Ops | Workshop intended to train Inspectors (Ops and AIR) on the Annex 6 and 8 requirements. Note: RNP is part of PBN Ops Approval course which is already scheduled for the week of Oct 19th in Beijing | A new ICAO course/workshop on EDTO will be soon available for delivery. It is anticipated to be held in Bangkok (ICAO APAC office) due to the large demand on this training. Other courses on RVSP/CAT II and III will be provided through the Flight Operations Safety Oversight Course scheduled to take place 22-26 August in Bangkok. RNP AR is covered by the PBN OPS Approval course which has already been delivered. | Multiple EASA Combined Flight Operations Subjects: RVSM, CAT II/III/EDTO/AOC Certification delivered in Maldives, Nepal, and India. Multiple EASA Combined Airworthiness Subjects: RVSM, CAT II/III, EDTO delivered in India, and Nepal |
| 7 | Recurrent Airworthiness Inspector | Recurrent training course for airworthiness inspectors including OJT | Discussions are taking place with EASA through their South Asia project to address this training need in order to avoid duplication | Multiple Airworthiness OJT and courses were provided to Member States through the COSCAP SA – EASA – SARI Joint Activity Plan 2017. These activities involved Ops Spec Approval AIR (RVSM, CAT II/III, EDTO; OJT Part 21, 25, Part M and 145; Human Factors for AIR. These courses were delivered in Bhutan, India, Nepal, Sri Lanka, Additional AIR courses will be provided in 2018 |
| 8 | Auditing Technique (Ops and Air) | Audit technique course required for operational inspectors to conduct audits on service providers | The CTA can deliver both the Audit Technique – generic course and also the Audit Technique (OPS) course. Other specialized Audit Technique courses (i.e. Maintenance, Aerodrome) will have to be sourced out. | The CTA has delivered the Audit Technique Courses (Generic and OPS) to Pakistan, and India. Bhutan, Nepal and Sri Lanka scheduled to receive the course in the spring 2018 Through the COSCAP SA – EASA – SARI Joint Activity plan, Audit Technique Courses for AIR were delivered in Bangladesh, India, and Nepal |
| 9 | Flight Simulator Evaluation | Technical training for the approval of Full Flight Simulators | To be out sourced to possible service providers | EASA Simulator Evaluation course delivered in India |
| 10 | Lead Auditor (AGA) | Technical Training for the leading role in conducting audits for aerodromes regulatory requirements | To be out sourced to possible service providers | To be scheduled in 2018 |
| 11 | AOC Certification - initial | Technical course required by technical inspectors | This training has been scheduled as part of the Flight Operations Safety Oversight course, which is scheduled for 22-26 August 2016 in Bangkok. The course will be provided by SAA. | Course was delivered on 22-26 August 2016 in Bangkok. In addition AOC Certification modules were included within the FOI initial courses provided by EASA in Sri Lanka |
| 12 | Flight Ops Inspector – Initial and recurrent | Technical training for Flight Operations Inspectors | A portion of this training has been scheduled through the Flight Operations Safety Oversight course, which will be held in Bangkok 22-26 August. Supplementary training will be scheduled at a later date. The CTA is planning on delivering FOI recurrent workshops in 2017. | EASA FOI Initial course was delivered in Sri Lanka |
| 13 | Cabin Safety - Initial/recurrent | Technical training for Cabin Safety Inspectors | An initial Cabin safety course has been scheduled for 15-19 August in Bangkok. This course may also count as a recurrent course. | An EASA Cabin Crew initial course was delivered in Bangladesh |
| 14 | Personnel Licensing | Technical training for personnel licensing inspectors | This course will be scheduled sometimes in the fall of 2016 by SAA. SAA will provide us the dates within the next couple of weeks. | Through COSCAP SEA, this course was delivered in BKK by SAA |
| 15 | Accident Investigation - Basic | Technical training for Accident Investigators | Singapore Academy offers this course EASA may also be able to provide this course | To be scheduled in 2018 |
| 16 | Accident Investigation - Advance | Technical training for Accident Investigators | Singapore Academy offers this course EASA may also be able to provide this course | Course to be sourced out and scheduled later in 2018 |
| 17 | ANS Inspector – Initial and recurrent | Technical Training for ANS Inspectors | Singapore Academy offers this course Capacity Matrix may apply | Course to be sourced out and scheduled for 2018 |
| 18 | Aerodrome Inspector – initial | Technical training for Aerodrome Inspectors | Singapore Academy offers this course EASA may be able to support this course Capacity Matrix may apply | Course to be sourced out and scheduled for 2018 |
| 19 | Wildlife Management | Technical training for Aerodrome Inspectors on how to control wildlife at aerodromes | Multiple sources available. Must source out to determine the most cost effective course to be provided | Course to be sourced out and scheduled for 2018 |
| 20 | Ramp Inspection | Technical training for both Flight Operations and Airworthiness Inspectors | This course is incorporated within the Flight Operations Safety Oversight course, which will be delivered in 22-26 August 2016. Supplementary training will be scheduled for Airworthiness through the EASA South Asia project | This course was included in the EASA SAFA ramp inspection courses as specified below |
| 21 | SAFA Inspection | Technical Training to conduct ramp inspections on Foreign Operators | Discussions are taking place with EASA through their South Asia project to address this training need in order to avoid duplication | EASA SAFA ramp inspection courses were delivered in Bangladesh, and India |
| 22 | Flight Ops Instructor | Train the trainers in developing and delivering Flight Operations courses | To be determined | To be sourced out and scheduled as time permits |
| 23 | Aerodrome Auditing | Technical course for the purpose auditing aerodromes | Singapore Academy to be approached | To be sourced out and scheduled in 2018. |
| 24 | Aerodrome Safeguarding | Technical training for aerodrome inspectors | Various sources. To be sourced out | To be sourced out and scheduled in 2018 |
| 25 | Part 145, 147 and Part M | Technical Training for Airworthiness Inspectors | Discussions are taking place with EASA through their South Asia project to address this training need in order to avoid duplication | These courses were delivered in Nepal (Part M) and Sri Lanka through the EU SA Partnership project |
| 26 | AMO Certification Initial | Technical Training for Airworthiness Inspectors | Discussions are taking place with EASA through their South Asia project to address this training need in order to avoid duplication | This course was integrated in the EASA AIR Initial courses that were provided in the Maldives and Bangladesh |
| 27 | Human Factors for Maintenance | Technical Training for Airworthiness Inspectors | Discussions are taking place with EASA through their South Asia project to address this training need in order to avoid duplication | This course was delivered in Bhutan by EASA through the Joint activity Plan 2017 |
| 28 | Designated Medical Examiner (DME) PEL | Technical Training for CAA officers involved with providing oversight to the Designated Medical Examiners | Course to be sources out. | This course was delivered in Bhutan through the Joint activity Plan 2017 |
|  | Safety Enhancements |  |  |  |
|  | Regional Aviation Safety Teams | CTA to support Member implementation of safety actions from SARAST and the RASG / APRAST. | Ongoing - Monitor implementation status of safety enhancements Focus is GASP safety priorities – runway safety, controlled flight into terrain (CFIT) and loss of control (LOC) | CTA attending SARAST, APRAST and RASG meetings on an on going basis |
|  | SARAST | SARAST: The CTA will report to the COSCAP-SA Steering Committee on the implementation status of safety enhancements. | To be presented to COSCAP-SA Steering Committee Meeting | On Going |
|  | SEIs | COSCAP-SA to develop a priority list for implementation of safety enhancement initiatives. | To be presented to COSCAP-SA Steering Committee Meeting | On Going |
|  | Other Safety Issues | In coordination with other COSCAPs submit Information Papers or Discussion Papers to the APRAST for emerging issues. | Ongoing – coordinate with COSCAP-SA Member States | On Going |
|  | Administration |  |  |  |
|  | Safety Team | COSCAP-SA will plan SARAST immediately following the APRAST meeting. COSCAP-SA will canvas members for agenda items in advance of the SARAST meeting. | Ongoing - SARAST Meeting to take place in September 2016. Exact dates to be confirmed. | On Going |
|  | Steering Committee Meeting | COSCAP-SA CTA will plan COSCAP-SA Steering Committee Meeting (SCM) in accordance with decision of the previous SCM. COSCAP-SA CTA will canvas members/safety partners for agenda items in advance of the SCM. | 25h COSCAP-SA Steering Committee Meeting is scheduled for July 19-21, 2016 All States have been canvassed and the agenda has been prepared for the 25th SCM | On Going |
|  | Cooperation |  |  |  |
|  | COSCAP Performance Measurement | The COSCAP project document does not include performance measurement Reporting to SCM is based against activity ex workshops, missions, courses, etc. related to priorities Observation that there should be improved performance measurement Current programme measurement is activity based ICAO has previously completed various forms of programme audit on COSCAPs worldwide ICAO concluded that a traditional approach to programme audit is not adequate to assess programme effectiveness. Development of a performance measurement framework is needed Once developed for a specific COSCAP, the performance measurement would be included in the programme document Significant differences exist between COSCAPs, requiring tailored performance assessments | ICAO Air Navigation Bureau, coordinated by the Implementation Support and Development Section (ISD), has responsibility for technical support to safety assistance activities, including COSCAPs, RSOOs as well as the newly formed Regional Aviation Safety Groups ISD has commenced work to develop a performance framework, with initial work available in 2014. | COSCAP-SA will monitor activity and participate as requested New Performance indicators and targets will been published in the new COSCAP SA PD Phase V Once published the programme will be measured using these new performance indicators and targets |

# Text boxes

COSCAP-SA 2018 Work Plan

Technical Assistance Matrix (TAM)